X API Control Group Pull

Goal: Collect panel data for ~8,000 "average" Twitter users that will act as our control group against the parents in our treatment group. Collect a snapshot of who the users are, plus a 3-year daily posting history centered on a sampled tweet from 2013–2018 matching the distribution of births in our treatment group.

Pipeline Overview:

Phase 1: Pull 20k seed tweets (2013–18) via weighted time-window sampling for a placebo birth date

- Deduplicate on author_id (make sure we have 20k distinct users)

Phase 1b: Manual spot check of 100 randomly sampled seed tweets

  - Confirm tweets appear organic (i.e., not bots), if not then re-sample

Phase 2: Pull user profiles for all 20k users

- Filter A: drop if account created < 18mo before seed tweet

- Filter B: drop if avg posts > 403/week since account creation (matches the max from treatment)

- Target: retain at least ~8k users

Phase 2b: Run data through a checkpoint to make sure it appears somewhat similar to treatment

Phase 3: Pull daily post counts over 3-year windows for “surviving” users after above filters

Phase 1 – Seed Tweet Collection

Endpoint: GET /2/tweets/search/all (documentation)

From the pull: One tweet per user — the "anchor" for their 3-year window. Fields collected: tweet_id, author_id, and created_at.

Query:

- -is:retweet -is:reply lang:en

- Sort_order: recency

Sampling Strategy

- Divide the 5-year period into 260 weekly windows.

- One 1-hour window is queried per week

  - Hour drawn randomly according to the day-of-week X hour-of-day distribution of the treatment sample’s timestamps (168 buckets, ex. Mon 8am, Mon 9am, …, Sun 10pm, Sun 11pm, etc.)

  - Control group’s time distribution should match the treatment. This should also help avoid over sampling high-frequency users.

Yearly-Matching: The 20k target is allocated across years proportionally to the treatment sample’s yearly distribution.

Per-week query logic:

- Draw a weighted random day-hour from the treatment timestamp distribution (chosen hour)

- Week start = Monday of that week (ex. 2013-01-07 00:00:00 UTC)

- Set start_time = that week’s start + chosen hour

- Set end_time = start_time + 1 hour

- Pull up to [week’s target N] from that window

- Deduplicate on author_id to make sure we have distinct users, add user to candidate pool

Cost: ~260 API calls = ~$1

Phase 1b – Manual spot check

Randomly sample 100 seed tweets from the full 20k candidate pool to make sure the tweets appear organic (not bots or advertisements). This is manual.

Phase 2 — User Profile Lookup + Filtering

Endpoint: GET /2/users (batch, 100 users per request) (documentation)

Per user traits to pull: username, description, created_at, public_metrics.followers_count, public_metrics.following_count, public_metrics.tweet_count, verified

Filters applied

- Filter A: Pre-period validity: Drop user if seed_tweet_date − account_created_date < 18 months. Keeps users with a full pre-window.

- Filter B: High-volume filter: Drop user if lifetime_tweet_count / account_age_in_weeks > 403.  Removes bots and power users.

  - Note: Threshold derived from the winsorized maximum avg weekly post rate in the treatment sample (1610.889 monthly posts / 4 = 402.7  403)

Estimated API calls: 200 (100 users/request X 20k users)

Cost: $200 ($0.010/user × 20k users)

Phase 2b – Check account stats

Review the filtered user profile data to make sure it matches the distributions of our treatment sample

- Distribution of seed tweet dates across 2013–2018

- Distribution of account creation dates

- Distribution of average weekly post rates — validate the 403/week cutoff

- Follower/following distributions

- Confirm surviving user count is sufficient (goal ~8k) — if not, return to Phase 1 and expand candidate pool

- Spot-check a handful of user profiles manually

Phase 3 takes the surviving list of profiles from this checkpoint 2b. Can manually trim here if needed

Phase 3 — Daily Post Volume (3-Year Panel)

Endpoint: GET /2/tweets/counts/all (documentation)

Output: Daily count time series for each user, covering 18 months before their seed tweet through 18 months after. Returns { date, count } for every day in the window — including 0s on days with no posts.

Two calls per user to separate post types:

| Call | Query | Output Column |
| --- | --- | --- |
| Call A | from:{user_id} -is:retweet -is:reply | original_quote_count |
| Call B | from:{user_id} (is:retweet OR is:reply) | retweet_reply_count |

Parameters per call:

- granularity=day

- start_time = seed tweet date − 18 months

- end_time = seed tweet date + 18 months

Estimated API calls: ~16,000 (2 calls x ~8k-20k users, depending on Phase 2b)

Cost: $160-400 ($0.010/request × 2 calls × 8k-20k users)

* 300 requests/15 min, 16k-40k requests, ~14-28 hours. This is where we would parallelize potentially across multiple API keys or batching calls in async code to stay within the rate limits

Cost Summary:

| Phase | Endpoint | Requests | Cost |
| --- | --- | --- | --- |
| Seed tweets | Tweets/search/all | ~40 | ~$1 |
| User profiles | Users (batch) | 200 | $200 |
| Daily Counts/Volume | Tweets/counts/all | 16,000-40,000 | $160-400 |
| Total |  |  | $360-600 |